## Gantt Chart Template
Project Breakdown Schedule
| PROJECT TITLE | Multiplayer Black Jack Game
[10 empty] | PHASE ONE: REQUIREMENTS | [27 empty] | PHASE TWO: DESIGN | [27 empty] | PHASE 3: IMPLEMENTATION + TESTING/MAINTENANCE
WBS NUMBER | TASK TITLE | TASK OWNER |  |  |  |  | START DATE | DUE DATE | DURATION | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
[10 empty] | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa
1 | Requirements Phase | Monisha | Daniel | Tochi | Sadhvik | Nikki |  | 2026-03-05
1.1 | SRS Document | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | WEEK 2 F: Initial SRS Doc + Working On It
1.1.1 | SRS : Purpose | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | WEEK 2 Sa: Definitions + Overview
1.1.2 | SRS : Overrall Description | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | WEEK 4 Su: Assumptions
1.1.3 | SRS : Specific Requirements | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | WEEK 4 Su: Modules
1.1.4 | SRS : Non-Functional Requirements | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | bar: WEEK 4 M
1.2 | Meeting Minutes Document | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | bar: WEEK 2 Sa to WEEK 3 M; WEEK 3 F to WEEK 4 Su; WEEK 4 T to WEEK 4 F
1.3 | Project Schedule Document | [5 empty] | 2026-02-05 | 2026-03-05 | 30 | WEEK 3 F: Organize Gantt
2 | Design Phase | [6 empty] | 2026-04-09
2.1 | DSD | [5 empty] | 2026-03-05 | 2026-04-09 | 34 | WEEK 1 T: Create Initial DSD Doc; WEEK 3 T: UI Interface
2.2 | Class Diagram | [5 empty] | 2026-03-05 | 2026-04-09 | 34 | WEEK 4 M: Class Diagram Adjustments
2.3 | Sequence Diagram | [5 empty] | 2026-03-05 | 2026-04-09 | 34 | bar: WEEK 4 T to WEEK 4 Th
2.4 | Meeting Minutes Document | [5 empty] | 2026-03-05 | 2026-04-09 | 34 | bar: WEEK 3 T; WEEK 4 T to WEEK 4 W
3 | Implementation Phase | [6 empty] | 2026-05-05
3.1 | [6 empty] | 2026-04-09 | 2026-05-05 | 26
3.2 | [6 empty] | 2026-04-09 | 2026-05-05 | 26
3.3 | [6 empty] | 2026-04-09 | 2026-05-05 | 26
3.4 | [6 empty] | 2026-04-09 | 2026-05-05 | 26
4 | Testing & Maintenance | [6 empty] | 2026-05-05
4.1 | [6 empty] | 2026-04-09 | 2026-05-05 | 26

## Try Smartsheet
Try Smartsheet for Free